## final bug report
component | Bug_id | summary | describtion | steps | test data | actual result | expected result | priority | severty | environment | status | attatchment
Login | BUG_01 | error message when login with empty fields not matched requirements | user enter empty username and password and cilck on login button the error message display incorrectly when it don't guide the user as required | go to swag lab demo website user click on login button withput fill username and password | url:"https://www.saucedemo.com"username :empty password :empty | error message:Epic sadface: Username is required | error message: username is required password is required | mid | low | laptop: HP stable wifi connection chrome V142 | open | https://drive.google.com/file/d/1N-4CpHdeCz_RFdUWm3J7K4h-pYyFg-K3/view?usp=sharing
| BUG_02 | login with username containing leading and trailing spaces shows incorrect error message | user enters username with leading and trailing spaces and valid password then clicks l ogin button, system rejects login but displays a generic authentication error message instead of a specific validation message for invalid username format | 1-go to swag lab demo website 2- user enter username with leading/trailing spaces " standa rd_user " 3- user enter password "secret_sauce" 4- user click login button | url:"https://www.saucedemo.com" username: " standard_user " password: secret_sauce | system rejected login but displayed generic error message "Epic sadface: Username and password do not match any user in this service" instead of indicating invalid username format | system should reject invalid username format and display a clear validation message indicating invalid username format | mid | low | laptop: HP stable wifi connection chrome V142 | open | Screenshot 2026-04-15 182446.png
| BUG_03 | password field does not provide show or hide visibility option | user enters password in login page but there is no eye icon or visibility toggle to allow user to view typed password before submitting | 1-go to swag lab demo website 2- user enter valid username 3- user enter password in password field 4- observe password field UI | url:"https://www.saucedemo.com" username: " standard_user " password: secret_sauce | password is always masked and no eye icon or visibility toggle is displayed | password field should provide an eye icon or show/hide toggle so user can view or hide entered password when needed | low | low | laptop: HP stable wifi connection chrome V142 | open | Screenshot 2026-04-15 182521.png
| BUG_04 | user can navigate back to login page after successful login using browser back button | after successful login, user is able to navigate back to the login page using the browser back button and then navigate again to the products page, indicating improper session navigation handling and lack of redirection control | 1- go to swag lab demo website 2- user login with valid credentials 3- user is redirected to products page 4- user click browser back button 5- user click browser back or forward button again | url:"https://www.saucedemo.com" username: " standard_user " password: secret_sauce | user was able to navigate back to login page and then navigate again to products page while session was still active | system should prevent navigation back to login page after successful login or automatically redirect user to products page | mid | mid | laptop: HP stable wifi connection chrome V142 | open | bandicam 2026-04-15 18-25-51-795.mp4
| BUG_05 | error message contains unclear and non-professional wording ("Epic sadface") | system displays an error message with informal and unclear wording when user attempts to access a protected page without being logged in, which does not meet professional and user-friendly standards | 1- go to swag lab demo website 2- user attempts to access protected page or perform invalid action without login 3- observe displayed error message | url:"https://www.saucedemo.com" username :empty password :empty | system displayed error message "Epic sadface: You can only access '/inventory.html' when you are logged in." which contains unclear and non-professional wording | system should display clear, professional, and user-friendly error message without informal or confusing wording | mid | low | laptop: HP stable wifi connection chrome V142 | open | Screenshot 2026-04-15 182017.png
cart function | cart_01 | App allows checkout with an empty cart | When the cart is empty, the checkout button is still clickable and proceeds to the checkout page. No validation message is displayed to prevent the user from continuing. | 1-go to swag lab demo website 2- enter username and password and click on login button 3-Go to products page 4-Ensure cart is empty 5-Open cart 6-Click 'Checkout' | url:"https://www.saucedemo.com" Username: standard_user Password: secret_sauce | user is directed to checkout information page | should be handled with an error message can't checkout with empty cart | high | high | labtop:lenovo stable wifi connection chrome V142 | open | https://drive.google.com/file/d/1k6-ymqgXeunWGfKatsviDCzmrBvk4A_O/view?usp=sharing
| cart_02 | No option to increase quantity for a product already added to cart | Once a product is added to the cart, no option to increase its quantity. The 'Add to cart' button is replaced by 'Remove' and no quantity field is available in the cart." | 1- go to swag lab demo website 2- enter username and password and click on login button 3-Go to products page 4-Add a product to cart 5-Go back to products page 6- Click 'Add to cart' on the same product again | url:"https://www.saucedemo.com" Username: standard_user Password: secret_sauce | button stays as 'Remove', quantity remains 1 | Quantity of the item increases to 2 in the cart | high | high | labtop:lenovo stable wifi connection chrome V142 | open | https://drive.google.com/file/d/1mHHc0ZXDhzd6KIJUCbtjX5TbSgdTqhTx/view?usp=sharing
product | BUG-P01 | Incorrect product details displayed (description and product name issues) | Some product details are not displayed correctly on the Products page. The backpack description appears incorrect (like code/method text), and the red t-shirt product name is not displayed properly. This affects the clarity and usability of product information. | 1- go to swag lab demo website 2- enter username and password and click on login button 3-Go to products page 4-check all product cards | url:"https://www.saucedemo.com" Username: standard_user Password: secret_sauce | 1-Backpack description appears as unreadable or incorrect text (like a method) Red t-shirt product name is incorrect or not properly displayed 2-Red t-shirt product name is incorrect or not properly displayed | 1-Product description should be clear, readable, and meaningful 2-Product name should be displayed correctly for all products | high | high | labtop:acer stable wifi connection chrome V142 | open | https://drive.google.com/file/d/1pKU8KkSxpjASxLuaDYqRi5F2NkTw7N7a/view?usp=sharing
| BUG-P02 | Sorting option resets after page reload | The selected sorting option on the Products page does not persist after reloading the page. The system resets it to the default sorting option instead of keeping the user’s selection. | "1-go to swag lab demo website 2- enter username and password and click on login button 3-Go to products page 4-add sorting method 5-reload the page | url:"https://www.saucedemo.com" Username: standard_user Password: secret_sauce | 1-page loads without lag 2-The selected sort option not remains as it is | 1-page loads without lag 2-The selected sort option remains as it is | mid | mid | labtop:acer stable wifi connection chrome V142 | open | https://drive.google.com/file/d/16g33LBInQxCofTBV0gpzu9TsuDx8v-1n/view?usp=sharing
| BUG-P03 | Footer and lower page UI not displayed correctly on product details page | The footer and lower page UI section are not displayed correctly on the product details page. The section appears missing or cut off, while it is displayed normally on other pages like the cart page. | 1- go to swag lab demo website 2- login with valid credentials 3- navigate to inventory page 4- click on any product name or product image to open product details page 5- scroll to the bottom of the product details page 6- observe the lower page UI and footer section | url:"https://www.saucedemo.com" Username: standard_user Password: secret_sauce | lower page UI/footer section was missing or cut off on product details page, while the same section displayed normally on cart page | product details page should display all UI elements correctly including product information, action buttons, lower page section, social media icons, and footer without truncation, missing area, or layout break | high | high | labtop:acer stable wifi connection chrome V142 | open | n/a
navigation | BUG-N01 | Product button does not reset to "Add to Cart" after removing item | The product action button does not update correctly after removing an item from the cart. Even when the cart becomes empty, the button still displays "Remove" instead of reverting to "Add to Cart", which causes confusion to the user and indicates a state management issue | 1- go to swag lab demo website 2- Log in with standard_user Password: secret_sauce 3- Add a product to the cart 4-click reset app state 5- Go back to the products page | url:"https://www.saucedemo.com" Username: standard_user Password: secret_sauce | cart becomes empty but product button still "Remove" instead of "Add to cart" | Reset product button state to "add to cart" | high | mid | labtop:hp stable wifi connection chrome V142 | open | https://drive.google.com/file/d/10SoonuIPkVvVCqWI_hzhuEwqFdvP3LiS/view?usp=sharing
| BUG-N02 | User is redirected to cart page without login | The application allows unauthenticated users to access the cart page directly without being redirected to the login page. This behavior violates access control rules and represents a potential security issue. | 1-Open the website swag lab demo without logging in by URL of the cart 2-Try to access the cart page | url:"https://www.saucedemo.com" Username: standard_user Password: secret_sauce | user is redirected to cart without login | User is redirected to login page | high | high | labtop:hp stable wifi connection chrome V142 | open | https://drive.google.com/file/d/1A0CYUEa8_QC8XikrRL8RYziu9eMCdTIK/view?usp=sharing
| BUG-N03 | Logout confirmation message is not displayed | When the user attempts to log out, the system logs them out immediately without displaying any confirmation message. This may lead to accidental logouts and negatively impacts user experience | 1- go to swag lab demo website 2- Click on Logout | url:"https://www.saucedemo.com" Username: standard_user Password: secret_sauce | User is logged out immediately | Confirmation message should appear before logout | mid | high | labtop:hp stable wifi connection chrome V142 | open | https://drive.google.com/file/d/1Dw1hG9YI0jv0ujyQ6lWcvgSnBuZm_xDb/view?usp=sharing
checkout | BUG-CO-001 | Error message appears only for the first empty field , not all required fields | the system does not properly validate all required fields on the Checkout Step One page. When multiple fields are left empty, the application only displays a validation error for the first empty field instead of identifying all missing required input | go to swag lab demo website Leave Last Name and Zip Code fields empty Enter First Name: John Delete First Name so all fields become empty Click Continue | url:"https://www.saucedemo.com" First Name: empty Last Name: empty Zip Code: empty | Only “Error: First Name is required” is displayed, even though other fields are also empty. | An error message should appear for all required empty fields (First Name, Last Name, Zip Code), or a combined validation message listing all missing fields. | mid | mid | labtop:hp stable wifi connection chrome V142 | open | https://drive.google.com/file/d/1Dw1hG9YI0jv0ujyQ6lWcvgSnBuZm_xDb/view?usp=sharing
| BUG-CO-002 | Checkout is allowed with an empty cart | The system allows users to proceed to the checkout process even when the shopping cart is empty. There is no validation or restriction preventing navigation to the Checkout Step One page without any products in the cart. | go to swag lab demo website Navigate directly to the Cart page Click on the Checkout button | url:"https://www.saucedemo.com" Cart State: empty cart User: standard_user (logged in) | User is redirected to Checkout Step One and then to the Overview page with no products or pricing. | User is redirected to Checkout Step One and then to the Overview page with no products or pricing. | high | high | labtop:hp stable wifi connection chrome V142 | open | https://drive.google.com/file/d/1Dw1hG9YI0jv0ujyQ6lWcvgSnBuZm_xDb/view?usp=sharing
| BUG-CO-003 | Zip Code field accepts alphabetic characters without validation. | The Zip Code input field does not enforce proper data validation and incorrectly accepts alphabetic characters. The system does not restrict input type or display an appropriate validation error message for invalid formats. | go to swag lab demo website go to checkout page Enter First Name: John Enter Last Name: Doe Enter Zip Code: ABCDE Click Continue | url:"https://www.saucedemo.com" First Name: John Last Name: Doe Zip Code: ABCDE | The system accepts the input and proceeds to the Overview page without validation | The system should reject non-numeric input and display a validation message such as “Zip Code must be numeric” | mid | mid | labtop:hp stable wifi connection chrome V142 | open | https://drive.google.com/file/d/1Dw1hG9YI0jv0ujyQ6lWcvgSnBuZm_xDb/view?usp=sharing
| BUG-CO-004 | First Name field accepts numbers and special characters without validation. | The First Name field does not validate input format and allows numbers and special characters. This indicates missing input validation rules for name fields, which should only accept alphabetic characters. | go to swag lab demo website go to checkout page Enter First Name: 123!@# Enter Last Name: Doe Enter Zip Code: 12345 Click Continue | url:"https://www.saucedemo.com" First Name: 123!@# Last Name: Doe Zip Code: 12345 | The system accepts the input and proceeds to the Overview page without any validation error. | The system should reject numeric and special characters in the First Name field. | mid | high | labtop:hp stable wifi connection chrome V142 | open | https://drive.google.com/file/d/1Dw1hG9YI0jv0ujyQ6lWcvgSnBuZm_xDb/view?usp=sharing